## Start here
Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding
Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding | Nature's Bidding
Audio production | Audio production | Audio production | Audio production | Audio production | Audio production | Audio production | Audio production
Tasks completed | Tasks completed |  | First milestone | First milestone |  | Open defects | Open defects
0 / 30 |  |  | 0 / 12 |  |  | 1
Pick one sound to start | Pick one sound to start | Pick one sound to start | Pick one sound to start | Pick one sound to start | Pick one sound to start | Pick one sound to start | Pick one sound to start
Hit impact | Hit impact |  | Parry | Parry |  | Bid submitted | Bid submitted
Listen to the existing hit sound. Test its timing and repetition in a round. | Listen to the existing hit sound. Test its timing and repetition in a round. |  | Parry from both sides. Check that a successful parry sounds once. | Parry from both sides. Check that a successful parry sounds once. |  | Submit a valid bid. Make sure it sounds different from a rejection. | Submit a valid bid. Make sure it sounds different from a rejection.
Listen to the existing hit sound. Test its timing and repetition in a round. | Listen to the existing hit sound. Test its timing and repetition in a round. |  | Parry from both sides. Check that a successful parry sounds once. | Parry from both sides. Check that a successful parry sounds once. |  | Submit a valid bid. Make sure it sounds different from a rejection. | Submit a valid bid. Make sure it sounds different from a rejection.
Listen to the existing hit sound. Test its timing and repetition in a round. | Listen to the existing hit sound. Test its timing and repetition in a round. |  | Parry from both sides. Check that a successful parry sounds once. | Parry from both sides. Check that a successful parry sounds once. |  | Submit a valid bid. Make sure it sounds different from a rejection. | Submit a valid bid. Make sure it sounds different from a rejection.
Your working tabs | Your working tabs | Your working tabs | Your working tabs | Your working tabs | Your working tabs | Your working tabs | Your working tabs
Sound tracker | Sound tracker |  | Milestones | Milestones |  | Listening tests | Listening tests
Sound tracker | Sound tracker |  | Milestones | Milestones |  | Listening tests | Listening tests
Effects reference | Effects reference |  | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week.
Effects reference | Effects reference |  | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week. | Update the stage after each session. Check milestone dates and open defects once a week.
Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done | Brief > Design > Review > Implement > QA > Done
The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today. | The reference and detailed workflow are below. You do not need to fill everything in today.
Workflow and reference | Workflow and reference | Workflow and reference | Workflow and reference | Workflow and reference | Workflow and reference | Workflow and reference | Workflow and reference
1. Set scope | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues. | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues. | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues. | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues. | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues. | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues. | Read Status Effects. Confirm each audio decision before making new sounds. The 47 gameplay effects do not automatically require 47 unique cues.
2. Audit existing events | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage. | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage. | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage. | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage. | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage. | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage. | Filter the tracker to Audit needed. Listen in Wwise and in Unity. Keep useful sounds, then set each row to the next actual stage.
3. Plan a small batch | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish. | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish. | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish. | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish. | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish. | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish. | Choose M1 tasks first. Enter an owner, due date and estimate. Suggested P1 means gameplay clarity, P2 means supporting feedback, P3 means optional polish.
4. Produce and review | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action. | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action. | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action. | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action. | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action. | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action. | Work through Brief, Design and Review. Record the DAW session, export location and variation count. Put review feedback in Blocker or next action.
5. Implement | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA. | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA. | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA. | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA. | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA. | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA. | Assign the event in Unity and confirm the trigger. Generate SoundBanks for the target platforms using the project workflow. Move the task to QA.
6. Test and finish | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result. | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result. | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result. | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result. | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result. | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result. | Run the acceptance test in the tracker. Record the build, date and result in QA log. Use Done only after QA passes and the reviewer accepts the result.
Daily | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed. | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed. | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed. | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed. | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed. | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed. | Update the stage and actual hours for the rows you touched. Write a specific next action when blocked, including the person or asset needed.
Weekly | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change. | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change. | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change. | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change. | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change. | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change. | Review milestone dates, unfinished P1 tasks and open defects with the team. Adjust scope or dates when dependencies change.
Stage meanings | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope. | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope. | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope. | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope. | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope. | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope. | Audit needed = inspect current work. Brief = agree the sound. Design = create it. Review = gather feedback. Implement = connect it. QA = test it. Done = accepted. Deferred = out of current scope.
Naming | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event. | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event. | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event. | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event. | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event. | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event. | Keep existing event names. New events can use Play_<Category>_<Purpose>. Use numbered lowercase variations, such as sfx_jump_01. Do not rename source WAVs merely to match an event.
Categories | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document. | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document. | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document. | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document. | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document. | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document. | SFX uses orange, UI blue, ambience olive, music indigo and dialogue pink. The category column follows the repository naming document.
Project handoff | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority. | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority. | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority. | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority. | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority. | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority. | Keep DAW source and exported audio discoverable through the tracker. Confirm export specifications with the project before batch exporting. Existing repository rules take priority.
Counts and capacity | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries. | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries. | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries. | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries. | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries. | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries. | The tracker contains 24 existing events and 6 proposed audio decisions. Summary formulas and dropdowns cover rows 5 through 204. Extend those ranges if the tracker grows beyond 200 entries.
Reading totals | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone. | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone. | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone. | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone. | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone. | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone. | Milestones count task rows. Stop events and decisions also count as tasks. This is not a WAV count. Deferred tasks remain assigned until you change their milestone.
Using Google Sheets | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details. | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details. | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details. | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details. | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details. | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details. | The tracker opens with everyday fields visible. Use the arrows above hidden columns to reveal production details.
Guide used | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project. | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project. | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project. | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project. | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project. | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project. | Greg Lester recommends milestone deliverables, ongoing tracking, a process covering creation through QA, and clear communication about dependencies. This workbook applies that approach to the current project.
Guide source | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio | https://www.gameaudiolearning.com/knowledgebase/organisation-and-pipelines-in-game-audio
Reference source | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Project sources | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026. | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026. | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026. | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026. | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026. | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026. | Current Wwise Events work units, the repository document Wwise naming and colors, and PlayerAudioFeedback / GameAudioController. Snapshot read September 20, 2026.
Scope notes | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed. | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed. | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed. | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed. | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed. | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed. | Status-effect descriptions and class names come from the reference. Blank classes remain blank. Suggested sounds, priorities, tests and milestone assignments need team review. No gameplay listening test was performed.

## Sound Effects Spreadsheet
Sound tracker
Choose one sound. Update its stage. Reveal columns I:T when you need production details.
Audio ID | Sound or task | Category | Priority | Stage | Owner | Milestone | Due date | Estimate hours | Actual hours | Wwise event | Trigger or brief | Variations | DAW session link | Export location or note | In-game acceptance test | Blocker or next action | QA result | Evidence | Source URL
AUD-001 | Forest ambience | Ambience | P2 | Audit needed |  | M2 |  |  |  | Play_AMB_Forest | Enter the forest arena |  |  | Record the DAW session and export folder after audit. | Enter, leave and revisit. Check looping and duplicate playback. |  | Not tested | Wwise Events / Ambience Work Unit.wwu
AUD-002 | Stop forest ambience | Ambience | P2 | Audit needed |  | M2 |  |  |  | Stop_AMB_Forest | Leave the forest arena |  |  | Stop event. No separate WAV required. | Leave during active playback. Check the tail and absence of stuck ambience. |  | Not tested | Wwise Events / Ambience Work Unit.wwu
AUD-003 | Lava ambience | Ambience | P2 | Audit needed |  | M2 |  |  |  | Play_AMB_Lava | Enter the lava arena |  |  | Record the DAW session and export folder after audit. | Enter, leave and revisit. Check looping and duplicate playback. |  | Not tested | Wwise Events / Ambience Work Unit.wwu
AUD-004 | Stop lava ambience | Ambience | P2 | Audit needed |  | M2 |  |  |  | Stop_AMB_Lava | Leave the lava arena |  |  | Stop event. No separate WAV required. | Leave during active playback. Check the tail and absence of stuck ambience. |  | Not tested | Wwise Events / Ambience Work Unit.wwu
AUD-005 | Combat event | Music | P2 | Audit needed |  | M2 |  |  |  | Play_Combat | Confirm intended relationship with music system |  |  | Record the DAW session and export folder after audit. | Compare this event with Game_Phase/Combat. Check accidental double playback. |  | Not tested | Wwise Events / Default Work Unit.wwu
AUD-006 | Lobby event | Music | P2 | Audit needed |  | M2 |  |  |  | Play_Lobby | Confirm intended relationship with music system |  |  | Record the DAW session and export folder after audit. | Compare this event with Game_Phase/Lobby. Check accidental double playback. |  | Not tested | Wwise Events / Default Work Unit.wwu
AUD-007 | Auctioneer voice | Dialogue | P2 | Audit needed |  | M2 |  |  |  | Play_DLG_Auctioneer | Auctioneer announcement |  |  | Record the DAW session and export folder after audit. | Run an auction. Check intelligibility under music and repeated announcements. |  | Not tested | Wwise Events / Dialogue Work Unit.wwu
AUD-008 | Adaptive music | Music | P1 | Audit needed |  | M2 |  |  |  | Play_MX_System | Music for game phases and maps |  |  | Record the DAW session and export folder after audit. | Traverse menu, lobby, bidding and both combat maps with two to four players. |  | Not tested | Wwise Events / Music Work Unit.wwu
AUD-009 | Stop music system | Music | P2 | Audit needed |  | M2 |  |  |  | Stop_MX_System | Stop the active music system |  |  | Stop event. No separate WAV required. | Verify the intended stop caller and fade behavior before approving. |  | Not tested | Wwise Events / Music Work Unit.wwu
AUD-010 | Man Mask explosion | SFX | P1 | Audit needed |  | M2 |  |  |  | Play_SFX_ManMask_Explosion | Timed mask explosion |  |  | Record the DAW session and export folder after audit. | Trigger Man Mask. Check explosion timing and audibility for all players. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-011 | Attack swing | SFX | P1 | Audit needed |  | M1 |  |  |  | Play_SFX_Woosh | Follow attack animation |  |  | Record the DAW session and export folder after audit. | Compare first swing, combos and misses. Check timing and repeated triggers. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-012 | Parry | SFX | P1 | Audit needed |  | M1 |  |  |  | Play_SFX_Parry | Communicate a successful parry |  |  | Record the DAW session and export folder after audit. | Parry from both sides. Confirm one audible response per successful parry. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-013 | Hit impact | SFX | P1 | Audit needed |  | M1 |  |  |  | Play_SFX_Hit | Confirm damage landed |  |  | Record the DAW session and export folder after audit. | Repeat light and heavy hits. Check variation, panning and rapid overlap. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-014 | Rock slide | SFX | P2 | Audit needed |  | M2 |  |  |  | Play_SFX_RockSlide | Dropping platform movement |  |  | Record the DAW session and export folder after audit. | Trigger platform drop. Check position, timing and replay behavior. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-015 | Jump | SFX | P2 | Audit needed |  | M1 |  |  |  | Play_SFX_Jump | Player leaves the ground |  |  | Record the DAW session and export folder after audit. | Jump with two players. Check timing, panning and repeated jumps. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-016 | Death | SFX | P1 | Audit needed |  | M1 |  |  |  | Play_SFX_Death | Player dies |  |  | Record the DAW session and export folder after audit. | Kill a player once. Confirm one sound and an audible tail after despawn. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-017 | Teleport | SFX | P1 | Audit needed |  | M2 |  |  |  | Play_SFX_Warp | Magician teleport |  |  | Record the DAW session and export folder after audit. | Equip Magician and teleport. Compare timing with departure and arrival. |  | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-018 | Fall | SFX | P1 | Audit needed |  | M1 |  |  |  | Play_SFX_Fall | Player falls out of bounds |  |  | Record the DAW session and export folder after audit. | Fall off the cliff. Confirm event posts and no null reference occurs. | Review PlayFall guard. See QA-001. | Not tested | Wwise Events / SFX Work Unit.wwu
AUD-019 | Bid adjustment | UI | P1 | Audit needed |  | M1 |  |  |  | Play_UI_Bid_Adjust | Increase or decrease a bid |  |  | Record the DAW session and export folder after audit. | Change bids rapidly in both directions. Confirm distinct responses without stacking. |  | Not tested | Wwise Events / UI Work Unit.wwu
AUD-020 | Bid submitted | UI | P1 | Audit needed |  | M1 |  |  |  | Play_UI_Bid_Submit | Accept a submitted bid |  |  | Record the DAW session and export folder after audit. | Submit a valid bid. Confirm one sound and no rejection sound. |  | Not tested | Wwise Events / UI Work Unit.wwu
AUD-021 | Bid rejected | UI | P1 | Audit needed |  | M1 |  |  |  | Play_UI_Bid_Reject | Reject an invalid bid |  |  | Record the DAW session and export folder after audit. | Attempt an invalid bid. Confirm feedback differs from success. |  | Not tested | Wwise Events / UI Work Unit.wwu
AUD-022 | UI click | UI | P2 | Audit needed |  | M1 |  |  |  | Play_UI_Click | Activate a control |  |  | Record the DAW session and export folder after audit. | Activate menus by mouse and controller. Check duplicate click sounds. |  | Not tested | Wwise Events / UI Work Unit.wwu
AUD-023 | UI focus | UI | P2 | Audit needed |  | M1 |  |  |  | Play_UI_Hover | Highlight a control |  |  | Record the DAW session and export folder after audit. | Move focus rapidly. Check sound rate and controller behavior. |  | Not tested | Wwise Events / UI Work Unit.wwu
AUD-024 | Shop purchase | UI | P1 | Audit needed |  | M1 |  |  |  | Play_UI_Shop_Purchase | Confirm an item purchase |  |  | Record the DAW session and export folder after audit. | Buy an item and attempt a failed purchase. Sound only on the intended result. |  | Not tested | Wwise Events / UI Work Unit.wwu
AUD-025 | Status acquired | UI | P2 | Brief |  | M2 |  |  |  |  | Confirm purchase or pickup feedback is enough |  |  |  | Acquire several passive effects. Avoid one new sound for every stat change. | Confirm need with design | Not tested | Proposed audio task from Status Effects reference | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
AUD-026 | Man Mask warning | SFX | P1 | Brief |  | M2 |  |  |  |  | Decide whether a warning is needed before detonation |  |  |  | Confirm duration and cancellation rules with design. | Confirm need with design | Not tested | Proposed audio task from Status Effects reference | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
AUD-027 | Star Tarot trigger | SFX | P2 | Brief |  | M2 |  |  |  |  | Decide sound for the star ability activation |  |  |  | Confirm the activation threshold and repeated-trigger rate. | Confirm need with design | Not tested | Proposed audio task from Status Effects reference | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
AUD-028 | Sun Tarot counter | SFX | P2 | Brief |  | M2 |  |  |  |  | Decide sound for the empowered parry |  |  |  | Distinguish a normal parry from the Sun response. | Confirm need with design | Not tested | Proposed audio task from Status Effects reference | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
AUD-029 | Moon Tarot glide | SFX | P2 | Brief |  | M2 |  |  |  |  | Decide whether glide needs a sustained sound |  |  |  | Check start, landing, effect removal and death stop conditions. | Confirm need with design | Not tested | Proposed audio task from Status Effects reference | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
AUD-030 | Health steal feedback | SFX | P3 | Brief |  | M2 |  |  |  |  | Decide a shared cue for life-steal effects |  |  |  | Check rapid hits and avoid masking hit impacts. | Confirm need with design | Not tested | Proposed audio task from Status Effects reference | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit

## Status Effects
Effects reference
Check whether an effect needs a new cue or can reuse a sound. Technical identifiers are hidden.
Effect Title | Internal ID | Description | Class Used | Audio decision | Related audio IDs | Suggested approach | Source URL
HP Up | hp_up | Get more health. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Damage Up | damage_up | Deal more damage. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Attack Speed Up | attack_speed_up | Attack faster. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Move Speed Up | move_speed_up | Move faster. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Parry Duration Up | parry_duration_up | Parry longer. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Parry Cooldown Down | parry_cooldown_down | Parry more. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Dash Distance Up | dash_distance_up | Dash farther. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Dash Cooldown Down | dash_cooldown_down | Dash more. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Crit Chance Up | crit_chance_up | Crit more often. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Crit Damage Multiplier Up | crit_damage_multiplier_up | Crit for more damage | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Momentum Strike | momentum_strike | The faster you move, the harder you hit. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Wombo Combo | wombo_combo | Combo more to deal more damage. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Thief | thief | Steal money from your opponents. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Heavy strike | heavy_strike | Hit twice as hard, move half as fast. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Glass Man | glass_man | Become fragile, but hit hard. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Feather Weight | feather_weight | Hit faster, but not as hard. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Coward | coward | Hide behind your shield. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Sprinter | sprinter | Move and dash faster. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Home Run | home_run | Hit slower, but harder | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Defensive Stance | defensive_stance | Move slower to tank more damage | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Absorber | absorber | Absorb enemy health. The higher the max health, the more you steal. | ComplexNumericalStatusEffectorSO | Review reuse | AUD-030 | Consider shared life-steal feedback. Confirm frequency and overlap with hits. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Fast Hands | fast_hands | Move faster the more money you carry. | ComplexNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Snake Mask | snake_mask | Snakes can't jump. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Turtle Mask | turtle_mask | Why not slow down? | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Butterfly Mask | butterfly_mask | A hit will send you flying | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Bear Mask | bear_mask | Big and slow. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Rabbit Mask | rabbit_mask | Small and delicate. | CompositeNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Bat Mask | bat_mask | Your controlls go batty. | ScriptedStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Bee Mask | bee_mask | Buffs for everyone! But not for you. | ApplyXToTargetPlayersStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
Man Mask | man_mask | The clock is ticking... | ScriptedStatusEffectorSO | Review existing + new | AUD-010, AUD-026 | Explosion event exists. Decide warning timing and cancellation separately. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Emperor Tarot | the_emperor_tarot | Double's your attacks' damage if you're the richest. | ScriptedStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Justice Tarot | the_justice_tarot | Claim an opponant's money when you hit them. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Weapon Tarot | the_weapon_tarot | You're armed and ready. | ScriptedStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Magician Tarot | the_magician_tarot | Who needs dashing when you can teleport? | ScriptedStatusEffectorSO | Review existing | AUD-017 | Warp event exists. Check timing and whether departure and arrival need separate layers. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Star Tarot | the_star_tarot | Move fast enough and the resulting stars will dazzle the competition. | ScriptedStatusEffectorSO | Review new cue | AUD-027 | Confirm when stars appear and whether one shared activation cue is enough. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Lovers Tarot | the_lovers_tarot | A big heart holds more health. | BasicNumericalStatusEffectorSO | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Sun Tarot | the_sun_tarot | Parry an opponant to unleash the wrath of the sun. | CompositeStatusEffectorSO ScriptedStatusEffectorSO ApplyStunOnActionStatusEffect ApplyDamageOnActionStatusEffect | Review new cue | AUD-028 | Reuse parry as a base. Decide whether the empowered response needs another layer. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Moon Tarot | the_moon_tarot | Jump higher and glide swiftly over terrain. | CompositeStatusEffectorSO ScriptedStatusEffectorSO GlideStatusEffect BasicNumericalStatusEffectorSO | Review new cue | AUD-029 | Review jump reuse and whether glide needs a loop with explicit stop conditions. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Devil Tarot | the_devil_tarot | Deal more critical hits and steal health too. | CompositeStatusEffectorSO | Review reuse | AUD-030 | Consider shared life-steal feedback. Confirm frequency and overlap with hits. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The World Tarot | the_world_tarot | After a kill, your health and damage output grow. So do you! | CompositeStatusEffectorSO ScriptedStatusEffectorSO ApplyXOnActionStatusEffect | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Fool Tarot | the_fool_tarot | You're crits do double damage, but your health decreases by 40. |  | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Chariot Tarot | the_chariot_tarot | You don't have to worry about knockback or attacking slowing you down. |  | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Hanged Man | the_hanged_man | Jump extra high and steal enemy health. |  | Review reuse | AUD-030 | Consider shared life-steal feedback. Confirm frequency and overlap with hits. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Empress Tarot | the_empress_tarot | Counterattacks become crits. |  | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The High Priestess | the_high_priestess | Regenerate health while not moving. |  | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Hermit Tarot | the_hermit_tarot | Send the others flying when you parry. |  | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit
The Tower Tarot | the_tower_tarot | If your health is greater, your hits become critical |  | Review reuse | AUD-025 | Start with shared acquisition feedback. Confirm whether gameplay needs another cue. | https://docs.google.com/spreadsheets/d/1lH4REzOzEWdbly2fVlv_ipqxtSUB278GweZunWTa760/edit

## Milestones
Milestones
Plan a small batch. Dates and owners are yours to choose.
Milestone | Deliverable | Target date | Owner | Assigned tasks | Done | Completion | Estimate hours | Actual hours | Exit criteria
M1 | Core combat and bidding |  |  | 12 | 0 | 0% |  |  | A playable round has clear hit, parry, death, bid and purchase feedback.
M2 | Effects, environments and music |  |  | 18 | 0 | 0% |  |  | Decide effect coverage. Test ambience stops, music transitions and auctioneer clarity.
M3 | Full playthrough and fixes |  |  | 0 | 0 |  |  |  | Pass a multiplayer playthrough on target builds. Close audio defects and record the tested build.
Notes | Hours stay blank until you enter estimates or actual time.
Move fixes into M3. Finish a task after an in-game listening test.

## QA log
Listening tests
Log what you heard and the build you tested. Close a defect after retesting its fix.
QA ID | Related audio IDs | Priority | Status | Owner | Build or platform | Test date | Steps or finding | Expected result | Actual result or evidence | Fix or retest notes | Source
QA-001 | AUD-018 | P1 | Open |  |  |  | Static code review. In PlayerAudioFeedback.PlayFall, a valid fallEvent returns before Post. | A valid event posts once. Missing references do not throw. | Investigate guard before testing. Not reproduced in a running build. |  | PlayerAudioFeedback.cs, PlayFall
QA-002 | AUD-008 | P1 | Not run |  |  |  | Move through menu, lobby, bidding and both maps. Eliminate players. | Correct music changes without duplicate playback or stuck states. |  |  | Suggested test
QA-003 | AUD-016 | P1 | Not run |  |  |  | Kill a player in host and client sessions. | One death sound, correct pan and audible tail after despawn. |  |  | Suggested test
QA-004 | AUD-002, AUD-004 | P2 | Not run |  |  |  | Leave and revisit both arenas. | Previous ambience stops and re-entry does not stack loops. |  |  | Suggested test
QA-005 | AUD-020, AUD-021 | P1 | Not run |  |  |  | Submit valid and invalid bids, then purchase an item. | Each action gives the correct feedback once. |  |  | Suggested test
QA-006 | All included audio | P1 | Not run |  |  |  | Play a complete round on each intended target platform with multiple players. | No missing events, stuck loops or audio errors. Dialogue and combat remain audible. |  |  | Suggested release test